## Sheet1
crtno | description_of_goods_works_and_services | category_of_procurement | qty | unit_of_measure | procurement_method | type_of_contract | allocated_amount | currency | source_of_funding | procuring_unit | requisition_division | requisition_unit | end_user_requisition_date | receipt_of_final_technical_requirements_date | preparation_of_tender_document_rfp_rfq_boqs_reoi_date | tender_publication_date | tender_closing_date | tender_opening_date | tender_evaluation_start_date | tender_evaluation_end_date | short_list_notice_publication_date | invitation_of_shortlisted_candidate_date | invitation_of_shortlisetd_canditates_closing_date | evaluation_of_bids_under_shortlist_method_start_date | evaluation_of_bids_under_shortlist_method_end_date | Purchase_Contracts Committee Approval Date | Evaluation Report Submission Date to SG | Evaluation Report Approval Date by SG | contract_vetting_submission_date | contract_vetting_approval_date | contract_amount | sg_asg_a_and_f_dhra_contract_approval_date | contract_signing_date | contract_duration | contract_end_date | business_unit | account_code | accounting_period | strategic_objective_analysis_code | coperating_partner_and_action_analysis_code | intervention_area_analysis_code | cost_centre_analysis_code | programme_action_components_analysis_code | output_analysis_code | main_activity_analysis_code | disbursement_category_analysis_code | budget_line_analysis_code
1 | M & E Consultancy | Services | 1 | Each | Request for Quotations/Proposals | Lump Sum | 10000 | USD | Member States | Procurement Unit | REARESA | Strategic Planning | 45017 | 45022 | 45027 | 45034 | 45055 | 45056 | 45061 | 45066 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | 45069 | 45074 | N/A | N/A | CMS | 5-7-75-0010 | 2022/001 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Laptop - Yvette M. KAOMA | Goods | 1 | Each | Request for Quotation (Low Value Procurement) | Lump Sum | 2500 | UGX | Member States | Procurement Unit | SPR | Strategic Planning | 45017 | 45022 | 45027 | 45034 | 45041 | 45042 | 45047 | 45052 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | 45055 | 45060 | N/A | N/A | CMS | 5-7-75-0010 | 2022/001 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | Laptop - Namwaka Muliwana MWAANGA | Goods | 1 | Each | Request for Quotation (Low Value Procurement) | Company based | 2500 | kwacha | Member States | Procurement Unit | INFRASTRUCTURE | Strategic Planning | 45017 | 45022 | 45027 | 45034 | 45041 | 45042 | 45047 | 45052 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBA | 45052 | 45057 | N/A | N/A | CMS | 5-7-75-0010 | 2022/001 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A